## 04oct
| Task |  | Description | Assigned To | Status | Start-Date | End-Date
USER REGISTRATION | Popup for User / guest | UI | Creating a popup Page for the User /guest | Bhaskar | Completed | 2023-09-28 | 2023-09-28
| Login Page | UI | Creating a Login Page for the User and validating | Bhaskar | Completed | 2023-09-19 | 2023-09-20
| login with mobile OTP | UI | otp validation by fireauth,and redirecting to Home | Bhaskar | Completed | 2023-09-20 | 2023-09-22
| Mobile number validating in database | API | Verifying the user details with the database with validation inputs to the fields without otp | Bhaskar | Completed | 2023-09-22 | 2023-09-22
| login with Email & Password | UI | Designing a Login page for Login with email and PassWord | Bhaskar | Completed | 2023-09-21 | 2023-09-22
| login with Email & Password | R-I | Integrating the Login with email page with api for user authentication nad login | Bhaskar | Completed | 2023-09-23 | 2023-09-23
| login with Email & Password - Validation | UI | Validation for input fields | Bhaskar | Completed | 2023-09-23 | 2023-09-23
| Email & password authenticating in database | API | Verifying the user details with the database with validation inputs to the fields | Bhaskar | Completed | 2023-09-24 | 2023-09-24
| Create Registration Form | UI | Design and create a user registration form with fields such as name , email / mobile , password , confirm password , etc. | Bhaskar | Completed | 2023-09-20 | 2023-09-22
| Registration Form | R-I | Integrating the registration form page to the API for storing the data into the database | Bhaskar | Completed | 2023-09-26 | 2023-09-27
| Input Validation for Regsitartion form | UI | Implement validation checks on user inputs ( e.g. , email format , password strength ) to ensure data integrity . | Bhaskar | Completed | 2023-09-27 | 2023-09-28
| Store User Data | API | Create a database or data storage system to store user registration data securely . Hash and salt passwords before storage . | Bhaskar | Completed | 2023-09-27 | 2023-09-28
| Cancellation of OTP after Clicking GetOtp | UI | Cancellation of OTP , after entring in to the otp input page | Bhaskar | Completed | 2023-10-04 | 2023-10-04
| Email Verification ( Optional ) | API | Send a verification email to the user's provided email address with a verification link . | Bhaskar | -----
Home / Nav-bar | Nav-bar | UI | Designing the Nav-bar component | RamaKrishna | In Progress | 2023-09-20 | 2023-09-26
| Logo | UI | displaying logo in Nav-bar of Home page | RamaKrishna | Completed
| Current Location Dsipalying in Nav-bar | R-I | Getting current location of user and displaying in the location box | Bhaskar | Completed | 2023-09-24 | 2023-09-25
| Search bar for products | R-I | Adding Functionality to the Search bar and showing the items respective to the search | Bhaskar | Not yet started
| My Subscriptions | UI | Designing the My-Subscriptions Page | RamaKrishna | Not yet started
| My Subscriptions | API | Getting the Subscriptions of the respective user fro DB | Siva | Completed | 2023-10-05 | 2023-10-05
| My Subscriptions | R-I | Adding Fucntionality to the My Subscriptions Button , redirecting to the Mysubscriptions Page with showing the Subscriptions of the user |  | Waiting for UI
| Cart | UI | Design the Cart Page to displa the Cart items of the respective user |  | Not yet started
| Cart | API | Inserting the Selected Product into the Cart table by UserId and ProductId and Added Date and with the Quantity or Size of product selected before Adding it to the Cart | Siva | have to check
| Cart | API | Deleting the Selected Product from Cart, if it was Deleted by user | Siva | have to check
| Cart | API | Getting the List of Products in the Cart table of respective user to display it in the Cart-UI | Siva | have to check
| Cart | R-I | integrating the List of products recived from API to display it in the Cart page , and adding the functionalities in it like( deleting the product from Cart , buy and add to WishList etc..) |  | Not yet started
| Wish List | UI | Design the Wish List Page to displa the wish list items of the respective user |  | Not yet started
| Wish List | API | Inserting the Selected Product into the Wish List table by UserId and ProductId and Added Date | Siva | Not yet started
| Wish List | API | Deleting the Selected Product from Wish List , if it was Deleted by user | Siva | Not yet started
| Wish List | API | Getting the List of Products in the Wish List of respective user to display it in the wish list | Siva | Not yet started
| Wish List | R-I | integrating the List of products recived from API to display it in the Wish List page , and adding the functionalities in it like( deleting the product from wish list , buy and add to cart etc..) |  | Not yet started
| User Icon and Name field | UI | Designing the User icon in the nav-bar & Getting the Current User Information and dispalying the name of the user | Bhaskar | In Progress | 2023-09-25 | 2023-09-25
| Profile Page | UI | Designing the Profile Page of the user |  | Waiting for UI Design
| Profile Page - Details | R-I | intgerating the user information to the profile page for disaplying the user data |  | Waiting for UI Design
| Profile Page -Editing | R-I | Giving editing option for the details of the user |  | Waiting for UI Design
| Profile Page -Editing | R-I | Giving validations for the inputs given in the Inpit fields of profile editing page |  | Waiting for UI Design
| Profile Page -Editing | API | Saving the edited data of user data into the Database | Siva | Completed
| Sign Out | UI | Redirecting to login by clearing the previous login user details and Redirecting to Login page | Bhaskar | Completed | 2023-09-25 | 2023-09-25
Home Page | Home Page | UI | Designing the Home Page |  | In Progress | 2023-09-20 | 2023-09-22
| Banner | UI | Dispalying the image in banner by changing (auto changing the images of products / offers) |  | In Progress | 2023-09-22 | 2023-09-22
| Products Buttons Nav | UI | Designing the buttons nav |  | Completed | 2023-09-20 | 2023-09-22
| Products Buttons Nav | R-I | Fucntionality of the buttons for displaying the selectd products in the render body |  | Completed | 2023-09-20 | 2023-09-22
| Categories | UI | Designing the Categories Display Row in the Home Page |  | In Progress | 2023-09-20 | 2023-09-22
| Categories | R-I | Getting the Categories Details and Displaying |  | Completed | 2023-09-25 | 2023-09-27
| Categories | R-I | When clicking the category , the respective categories products have to display in the products view page |  | Completed | 2023-09-25 | 2023-09-27
| Categories | API | Inserting the new category items into category table |  | Completed | 2023-09-20 | 2023-09-22
| Categories | API | Creating and API for getting the list of categories with Images |  | Completed
| Best-Sellers - Displaying | UI | Designing the Best-Sellers Display Row in the Home Page |  | In Progress | 2023-09-20 | 2023-09-21
| Best-Sellers - Displaying | R-I | Getting the Best Selling Products Details and Displaying |  | In Progress
| Best-Sellers - Displaying | R-I | When clicking the selected product , the respective product detail view has to display in the product detail view page |  | Not yet started
| Brands- Displaying | UI | Designing the Brands Display Row in the Home Page |  | Completed | 2023-09-20 | 2023-09-22
| Brands- Displaying | R-I | Getting the Brands of the Products Details and Displaying |  | Completed | 2023-09-28 | 2023-09-28
| Brands- Display-Functionality | R-I | When clicking the selected brand , thr products of respective brand have to show in the products display page |  | Completed | 2023-09-04 | 2023-09-06
| Brands | API | Creating and API for inserting the Brands and also for retrieving the Brands with Images |  | Completed | 2023-09-28 | 2023-09-28
Products | Products Page | UI | Designing the products page along with left side filter bar | Bhaskar | In Progress | 2023-10-02 | 2023-10-06
| Products Filter Side-bar | UI | Designing the products side filter bar to provide the filter options | Bhaskar | In Progress
| Product insert | API | API for inserting the New Products into the products table | Bhaskar | Completed | 2023-10-03 | 2023-10-06
| List Of Products | API | API for Getting the List of Products from the table to show it in the products Page | Bhaskar | Completed
| Products Display | R-I | Displaying the products in the body of page along with Details and Images | Bhaskar | Completed | 2023-10-03 | 2023-10-06
| Brand Filter | R-I | Displaying the products in the body of page by Brand filter selected by user along with details and Images | Bhaskar | Completed
| Size Filter | R-I | Displaying the products in the body of page by Size filter selected by user along with details and Images | Bhaskar | Not yet started
| categories Button | R-I | Adding Fucntionality to the buttons in the Categories , so that the particular Categories of products ahev to be displayed | Bhaskar | Not yet started
| Sorting Fucntionality | R-I | Adding functionality to the Sorting of products as (Price -Low to High , viceversa…etc) | Bhaskar | Not yet started
| Ratings Display | API | Getting the Ratings of the products to display it in the Rating Icon | Siva | In Progress
| Ratings Display | R-I | Displaying the Rating of product in the rating field | Bhaskar | Not yet started
| Adding to Wish List | R-I | after clicking the wishlist button , the product have to add to the wishlist of respective user | Bhaskar | Not yet started
| Add to Cart | R-I | By clicking ther Add to cart buttonn , the product with selected size have to be inserted into the cart table with respective userId and ProductId along with selected size | Bhaskar | Not yet started
| Quantity Selection of Product | R-I | Selecting the quantity of each product , and price of particular quantity should be displayed in the price sending the qty to the cart if added to cart or Subscription Page | Bhaskar | Completed | 2023-10-03 | 2023-10-06
| Subscription | R-I | After Clicking the subscription Redirecting to the subcription page along with the product with the selected quantity and Price | Bhaskar | Completed | 2023-10-04
| Add to Cart | R-I | Fucntionality of the button to add the item to the cart with the size selected | Bhaskar | In Progress
| Add to Cart | API | Adding the selected item to cart and storing in the DB of the user | Siva | Completed
| Review along with Rating | API | Inserting the Review/ Comment of product into the review/rating table by userId | Siva | In Progress
| Review along with Rating | API | Getting the Reviews/ Commenst of products from the table of the by the Product Id | Siva | In Progress
Individual Product View | Product DetailView | UI | Designing the product detail view page for Displaying the image and details of Products(name, price, quantity) | Siva | Completed
| Cart Fucntionality | R-I | adding item to the cart if cart button is clicked | RamaKrishna | In Progress
| Similar Prodcuts Div | UI | Designing the similar products row and ading scrolling functionlity for the row (products) | RamaKrishna | In Progress
| Similar Prodcuts Div | R-I | getting the similar products by doing filter and displaying it in the similar products row | RamaKrishna | In Progress
Subscription Pop-Up | Pop Up for Subscription | UI | Displaying the Respective Product with Image with selected quantity along with Price and Types of Subscription i.e; (Single day, Weekly, Monthly) with their respective prices after clicking Subscription button provided on product display page | Bhaskar | Completed | 2023-10-05 | 2023-10-06
| Subscription selection | API | Retrieving subscriptions data to show in the subscription popup for the respecgtive products | Siva | Completed | 2023-10-05 | 2023-10-06
| Qyuantity Change | R-I | Changing the quantity of the product for the user requirement and the respective calculation for the Order Quantity and subscription amount Have to changes | Bhaskar | Completed | 2023-10-05 | 2023-10-06
| Going Back / Cancelling the the popup | UI | Incase the user want's to go back Exit button is provided in popup and the item should have to be in cart | Bhaskar | Completed | 2023-10-05 | 2023-10-06
| Selected product Details | R-I | Displaying the details of the Product such as Price, Image and their Subscription Amount of weekly, monthly, yearly | Bhaskar | Completed | 2023-10-05 | 2023-10-06
Subscription / Order | Subscription Details Storing | API | Saving the subscription details afetr successful subscription of the user along with the order id , order details such as Adress,start date ,end date, amount, quantity , size of product, location ( separately in the order table and users subscriptions table) | Siva | Not yet started
| Subscription selection | API | Retrieving subscriptions data to show in the subscription popup for the respecgtive products | Siva | Completed
| Order Details Storing | API | Saving the Order details into Order table and into the Order Items table along with the Neccesary Data | Siva | Not yet started
| Quantity Change | R-I | Changing the quantity of the product for the user requirement and the respective calculation for the Order Quantity and subscription amount Have to changes | Bhaskar | Completed
| Going Back / Cancelling the the popup | UI | Incase the user want's to go back Exit button is provided in popup | Bhaskar
| Selected product Details | R-I | Displaying the details of the Product such as Price, Image and their Subscription Amount of weekly, monthly, yearly | Bhaskar | Completed
Address | Address | API | Create an adress table by using the USerID as Foreign key to store the addresses of the users | Siva | Completed | Not yet started | Not yet started
| Location Page | UI | Design a location page for selecting the location on the google map and entering sufficient the details of address | Bhaskar | Completed | 2023-10-06 | 2023-10-12
| Add Address | API | Storing the New address created by the user | Siva | Completed | 2023-10-10 | 2023-10-12
| Edit Address | API | Editing the saved Address by the user ID and the Address ID | Siva | In Progress
| Get Address | API | Getting the Saved Addresses of the particualr user | Siva | Completed | 2023-10-10 | 2023-10-12
| User Delivery Location Storage | API | The Delivery Address Mentioned by the user has to store in the database for the purspose of giving it to the delivary man | Siva | Completed | 2023-10-10 | 2023-10-12
| Precise location | UI | precise location of the user getting from embedded map on the location page |  |  | 2023-10-10 | 2023-10-12
| Validation and storing the data | R-I | validating the user Inputs and storing the Address data in database of address table |  |  | 2023-10-10 | 2023-10-12
User Payment | Payment page | UI | Paymnet page for the user for which type of transaction he /her wants to make
| Razorpay Payment details | API | Creating Razorpay Test Account and creating KeyId | Siva
| Razorpay | API | Razorpay Payment Gateway for the calling the razorpay payment api from the backend using asp.net web api | Siva
| Payment Details | API | Saving the Payment data along with the order details after placing a successful order and if the payment was failed due to RAZORPAY issue and the amount has been debited from customer , then the failed transaction details also have to be stored in the table in the category of FAILED TRANSACTION | Siva
| Payment Summary | API | Generating the payment & Subscription Summary after the successful or Failed payment o f subscription in PDF format | Siva
| Razorpay | R-I | Integrating the razorpay react code provided on docs of react raorpay with our fields
Products Page : Side- bar | Filter-nav | UI | Design the filter side-nav in Products display page | Bhaskar | Completed | 2023-10-04
| Brand - Names for Filters | R-I | Displaying the Brand for selecting (Filters) and Filter the Products as per Selection | Bhaskar | Not yet started | 2023-10-04 | 2023-10-06
| Quantity Filter | R-I | Displaying the Quantites in list view for filter and Filter the Products as per Selection | RamaKrishna | Not yet started
| Ratings Filter | R-I | Displaying the Ratings in list view for filter and Filter the Products as per Selection | RamaKrishna | Not yet started

## Sheet2 (2)
| Task |  | Description | Status | Assigned To
USER REGISTRATION | Login Page | UI | Creating a Login Page for the User and validating | completed |  | 3
| Authenticate Login | API | Verifying the user details with the database with validation inputs to the fields without otp | completed |  | 8
| Create Registration Form | UI | Design and create a user registration form with fields such as name , email / mobile , password , confirm password , etc. | completed |  | 3
| Registration Form | API | Design and create a user registration form with fields such as name , email / mobile , password , confirm password , etc. | completed |  | 3
| Input Validation | UI , API | Implement validation checks on user inputs ( e.g. , email format , password strength ) to ensure data integrity . | completed |  | 1
| Generate OTP ( Optional ) | UI | If allowing registration via mobile number , generate and send an OTP ( One - Time Password ) for verification . | completed |  | 3
| Store User Data | API | Create a database or data storage system to store user registration data securely . Hash and salt passwords before storage . | completed |  | 3 | 6
| Email Verification ( Optional ) | API | Send a verification email to the user's provided email address with a verification link . | completed |  |  |  | 31.25
| Mobile Number Verification ( Optional ) | UI , API | Verify the mobile number by comparing the entered OTP with the generated OTP . | completed |  | 2
| Handle Duplicate Entries | API | Check if the email / mobile number is already registered to prevent duplicate accounts . | pending |  | 1
| User Profile Setup ( Optional ) | UI, API | Allow users to set up their profiles with additional information like profile pictures , bios , etc.
USER PROFILE | Design User Profile Interface | UI | Create a user - friendly interface that allows users to view and edit their profile information |  |  | 6
| Create Database or Data Storage | API | Set up a database or data storage system to securely store user profile data and address information . |  |  | 2
| User Registration Integration | UI/ API | Integrate user profile management with the registration / authentication system . |  |  | 3
| Profile Information Fields | UI | Define the fields and information that users can input and edit in their profiles ( es , name , email , phone number , profile picture , etc. ) |  |  | 6
| Edit Profile Information | UI / API | Implement functionality for users to edit their profile information , Including password changes if needed and cahnging in database |  |  | 2
| Address Management | UI / API | Allow users to add , edit , and delete shipping addresses associated with their profie |  |  | 1
| Validation and Verification |  | Implement validation checks on user inputs to ensure data Integrity and accuracy . |  |  | 1
| Profile Picture Upload ( Optional ) |  | Enable users to upload and change their profile pictures |  |  | 2
| Default Shipping Address |  | Allow users to set a default shipping address for convenience during the checkout process |  |  |  | not needed now
| Address Autocomplete ( Optional ) |  | Implement address autocomplete or lookup festures to almpity address entry .
| Password Reset ( Options ) |  | Provide users with the ability to reset their passwords through their profile settings |  |  | 3
| Security Messures |  | Implement security measures to protect user dats , including encryption and secure transmission .
| Mobile Responsiveness ( Optional ) |  | Ensure the user profile interface is responsive and usable on mobile devices . |  |  |  | not needed now
| User Authentication |  | Implement user authentication to ensure that only the authorized user can access and edit their profile |  |  |  | not needed now
| Profile Privacy Settings ( Optional ) |  | Allow users to customize their privacy settings , such as who can view their profile and contact information . |  |  |  | not needed now
| Address Book Export ( Optional ) |  | Offer the option to export the user's address book in downloadable formats ( eg , CSV ) |  |  |  | not needed now
| User Notifications ( Options ) |  | Send email or push notifications to users regarding profile updates or security - related activities . |  |  | 3
PRODUCTS | Define Product Categories |  | Create a list of product categories and creating an UI for subscribers to show ( e.g. , groceries , electronics , clothing ) for organization . |  |  | 8
| Create Database or Data Storage |  | Set up a database or data storage system to store product information securely . |  |  | 1
| Add Products |  | Populate the database with product data , including names , descriptions , prices , images , and availability status . |  |  | 16
| Implement Category Filters |  | Develop functionality to filter products by category , allowing users to view products by type . |  |  | 12
| Implement Search Functionality |  | Add a search bar that enables users to search for products by keywords , names , or descriptions . |  |  | 5
| Implement Sorting Options |  | Provide options for users to sort products by price , name , availability , etc. |  |  |  | not needed now
| Display Product List |  | Create a user interface to display a list of products , organized by categories , with images and brief information . |  |  | 6
| Pagination ( if needed ) |  | Implement pagination to display a limited number of products per page and allow users to navigate through pages . |  |  | 3
| Product Detail Page |  | Create a product detail page that displays comprehensive information about a selected product , including images , descriptions , prices , and availability status . |  |  | 8 | have to show with the images in sliding part
| Add to WishList Functionality |  | If an e - commerce component is included , allow users to add products to their shopping cart for future purchase . |  |  | 5
| Reviews and Ratings ( Optional ) |  | Include user - generated reviews and ratings for products if desired . |  |  | 5
| Product Availability Alerts ( Optional ) |  | Implement notifications or alerts for users when a product becomes available if it was previously out of stock
| Related Products ( Optional ) |  | Suggest related or similar products to users based on their current selection . |  |  | 5 | when gone to product detail page only
| Implement User Authentication ( Optional ) |  | If user accounts are involved , integrate user authentication to track user interactions and personalize the experience .
SHOPPING CART | Design Shopping Cart Interface |  | Create a user - friendly shopping cart interface that displays added products , quantities , and prices . |  |  | 3
| Add to Cart Functionality |  | Implement the ability for users to add products to their shopping cart from the product catalog . |  |  | 2
| Remove from Cart Functionality |  | Allow users to remove products from their shopping cart . |  |  | 2
| Display Cart Contents |  | Show a list of products in the shopping cart with details like name , quantity , price , and subtotal . |  |  | 3
| Calculate Cart Total |  | Calculate and display the total price of all items in the shopping cart . |  |  | 3
| Update Quantity |  | Enable users to update the quantity of items in their cart , adjusting the subtotal and total price . |  |  | 3
| Proceed to Checkout |  | Create a " Proceed to Checkout " button that allows users to move to the checkout process .
| Implement Checkout Process ( Optional ) |  | Develop a complete checkout process , including user information , shipping , and payment .
| Save Cart Data ( Optional ) |  | Implement a way to save the shopping cart data for users who are logged in or using persistent carts .
| Apply Discounts and Coupons ( Optional ) |  | Include the ability for users to apply discounts or coupons to their cart total . |  |  | 10
| Empty Cart |  | Provide an option for users to clear their entire shopping cart . |  |  | 1
| Continue Shopping |  | Add a " Continue Shopping " button to let users go back to the product catalog . |  |  | 1
| Handle Out - of - Stock Items ( Optional ) |  | Notify users and handle cases where a product becomes out of stock after being added to the cart . |  |  | 3 | status/ remark / highlight of item label shoukld be taken
| Guest Checkout ( Optional ) |  | Allow users to check out as guests without requiring user registration . |  |  |  | 3
| Order Confirmation ( Optional ) |  | Display an order confirmation page after successful checkout with order details and a receipt . |  |  | 6
| User Authentication ( Optional ) |  | Implement user authentication to associate carts with user accounts for registered users . |  |  | 2
CHECK OUT & PAYMENT | Collect Shipping Information |  | Design and implement forms for users to enter shipping details, including address and contact information. |  |  | 4
| Validate Shipping Information |  | Implement validation checks on shipping information to ensure accuracy and completeness. |  |  | 1
| Provide Payment Options |  | Offer various payment options, including credit card, debit card, net banking, cash on delivery, etc. |  |  | 16
| Implement Payment Gateway Integration |  | Integrate a payment gateway to facilitate secure and real-time payment processing. |  |  | 4
| Calculate Order Total |  | Calculate the total order amount, including product prices, taxes, and shipping fees. |  |  | 3
| Display Order Summary |  | Show users an order summary, including itemized details, shipping costs, and the total amount to be paid. |  |  | 2
| Secure Payment Handling |  | Implement security measures to protect payment data during transmission and storage. |  |  |  | no idea
| Handle Payment Errors |  | Create error handling mechanisms to address payment failures and provide clear error messages to users. |  |  |  | no idea
| Confirm Order |  | Allow users to review their order, payment method, and shipping details before confirming the purchase. |  |  |  | extra
| Place Order |  | Execute the payment transaction and place the order once the user confirms their purchase. |  |  | 3
| Order Confirmation Page |  | Display an order confirmation page with a summary, order number, and confirmation message to the user. |  |  | 3
| Send Order Confirmation Email |  | Send a confirmation email to the user with details of their order , estimated delivery date , and payment receipt . |  |  | 4
| Guest Checkout ( Optional ) |  | Allow users to check out as guests without requiring user registration .
| User Authentication ( Optional ) |  | Implement user authentication to associate orders with user accounts for registered users .
| Handle Multiple Payment Gateways ( Optional ) |  | If offering multiple payment gateways , configure and manage their integration .
| Compliance with Payment Regulations ( Optional ) |  | Ensure compliance with payment industry regulations , such as PCI DSS , if applicable .
ORDER | Design Order History Interface |  | Create a user interface that allows users to view their order history , including past and current orders . |  |  | 4
| Store Order Data |  | Set up a database or data storage system to securely store order information , including order items , dates , and statuses . |  |  | 2
| Send Order Confirmation Emails |  | Automate the sending of order confirmation emails to users after a successful purchase . |  |  | 3
| Implement Order Tracking |  | Provide an order tracking system that allows users to monitor the status and progress of their orders . |  |  |  | later
| Display Order Detall |  | Cre detalled er view that displays order items , quantities , prices , shipping details , and total cost . |  |  | 5
| Order Status Updates |  | implement mechanisms for updating and displaying order statuses , Including " Processing , " " Shipped , " " Delivered , " etc. |  |  | 16
| Tracking Information ( Optional ) |  | Offer shipment tracking Information from third - party carriers ( e.g. , FedEx , UPS ) If applicable . |  |  |  | later
| Handling Returns and Refunds ( Optional ) |  | Develop processes for managing return requests , processing refunds , and updating order status accordingly . |  |  |  | later
| Print Order Invoices ( Optional ) |  | Allow users to generate and print invoices for their orders for record - keeping purposes . |  |  | 8
| Order Cancellation ( Optional ) |  | implement a system for users to request order cancellations and update order status accordingly . |  |  | 6
| Notifications and Alerts ( Optional ) |  | Send email or push notifications to users regarding order status changes or delays in shipping .
| Order Export ( Optional ) |  | Provide an option for users to export their order history in downloadable formats ( e.g. , PDF , CSV ) . |  |  |  | not need now
| Mobile Responsiveness ( Optional ) |  | Ensure the order history Interface is responsive and usable on mobile devices .
| User Authentication ( Optional ) |  | Implement user authentication to associate orders with user accounts for registered users .
| Customer Support Integration ( Optional ) |  | integrate customer support tools or chat for users to inquire about their orders or request assistance . |  |  |  | not need now

## Sheet1
Task Description Status
User Registration and Authentication | User registration with email or mobile number. User authentication (login/logout) with password or OTP.
Product Catalog | Display a list of products categorized by type (e.g., groceries, electronics, clothing). Allow users to search for products. Display product details, including images, descriptions, prices, and availability.
Shopping Cart | Allow users to add/remove products to/from their shopping cart. Display the total price and quantity of items in the cart. Enable users to update quantities and proceed to checkout.
Checkout and Payment | Collect shipping information (address, contact details). Provide various payment options (credit card, debit card, net banking, cash on delivery, etc.). Implement payment gateway integration for secure transactions.
Order Management | Allow users to view their order history. Send order confirmation emails to users. Enable order tracking and status updates.
User Profile | Allow users to edit their profile information. Store and manage user addresses for shipping.
Admin Panel | Provide an admin dashboard for managing products, categories, and inventory. Manage user accounts, orders, and customer support.
Ratings and Reviews | Allow users to rate and review products. Display product ratings and reviews to other users.
Notifications | Send email or push notifications for order updates, promotions, and discounts. Implement subscription for newsletters and updates.
Wishlist | Allow users to add products to their wishlist. Enable users to move wishlist items to their cart
Recommendations and Personalization
Search and Filters
Security and Privacy
Scalability and Performance
Mobile Apps
Customer Support
Analytics and Reporting
Marketing and Promotions
Shipping and Logistics
Returns and Refunds
Reviews and Feedback
Legal Compliance

## Sheet2
| Task | Description
USER REGISTRATION | Create Registration Form | Design and create a user registration form with fields such as name , email / mobile , password , confirm password , etc.
| Input Validation | Implement validation checks on user inputs ( e.g. , email format , password strength ) to ensure data integrity .
| Generate OTP ( Optional ) | If allowing registration via mobile number , generate and send an OTP ( One - Time Password ) for verification .
| Store User Data | Create a database or data storage system to store user registration data securely . Hash and salt passwords before storage .
| Email Verification ( Optional ) | Send a verification email to the user's provided email address with a verification link .
| Mobile Number Verification ( Optional ) | Verify the mobile number by comparing the entered OTP with the generated OTP .
| Handle Duplicate Entries | Check if the email / mobile number is already registered to prevent duplicate accounts . | unique datatype in sql
| User Profile Setup ( Optional ) | Allow users to set up their profiles with additional information like profile pictures , bios , etc.
USER PROFILE | Design User Profile Interface | Create a user - friendly interface that allows users to view and edit their profile information
| Create Database or Data Storage | Set up a database or data storage system to securely store user profile data and address information .
| User Registration Integration | Integrate user profile management with the registration / authentication system .
| Profile Information Fields | Define the fields and information that users can input and edit in their profiles ( es , name , email , phone number , profile picture , etc. )
| Edit Profile Information | Implement functionality for users to edit their profile information , Including password changes if needed .
| Address Management | Allow users to add , edit , and delete shipping addresses associated with their profie
| Validation and Verification | Implement validation checks on user inputs to ensure data Integrity and accuracy .
| Profile Picture Upload ( Optional ) | Enable users to upload and change their profile pictures
| Default Shipping Address | Allow users to set a default shipping address for convenience during the checkout process
| Address Autocomplete ( Optional ) | Implement address autocomplete or lookup festures to almpity address entry .
| Password Reset ( Options ) | Provide users with the ability to reset their passwords through their profile settings
| Security Messures | Implement security measures to protect user dats , including encryption and secure transmission .
| Mobile Responsiveness ( Optional ) | Ensure the user profile interface is responsive and usable on mobile devices .
| User Authentication | Implement user authentication to ensure that only the authorized user can access and edit their profile
| Profile Privacy Settings ( Optional ) | Allow users to customize their privacy settings , such as who can view their profile and contact information .
| Address Book Export ( Optional ) | Offer the option to export the user's address book in downloadable formats ( eg , CSV )
| User Notifications ( Options ) | Send email or push notifications to users regarding profile updates or security - related activities .
PRODUCTS | Define Product Categories | Create a list of product categories ( e.g. , groceries , electronics , clothing ) for organization .
| Create Database or Data Storage | Set up a database or data storage system to store product information securely .
| Add Products | Populate the database with product data , including names , descriptions , prices , images , and availability status .
| Implement Category Filters | Develop functionality to filter products by category , allowing users to view products by type .
| Implement Search Functionality | Add a search bar that enables users to search for products by keywords , names , or descriptions .
| Implement Sorting Options | Provide options for users to sort products by price , name , availability , etc.
| Display Product List | Create a user interface to display a list of products , organized by categories , with images and brief information .
| Pagination ( if needed ) | Implement pagination to display a limited number of products per page and allow users to navigate through pages .
| Product Detail Page | Create a product detail page that displays comprehensive information about a selected product , including images , descriptions , prices , and availability status .
| Add to Cart Functionality | If an e - commerce component is included , allow users to add products to their shopping cart for future purchase .
| Reviews and Ratings ( Optional ) | Include user - generated reviews and ratings for products if desired .
| Product Availability Alerts ( Optional ) | Implement notifications or alerts for users when a product becomes available if it was previously out of stock
| Related Products ( Optional ) | Suggest related or similar products to users based on their current selection .
| Implement User Authentication ( Optional ) | If user accounts are involved , integrate user authentication to track user interactions and personalize the experience .
SHOPPING CART | Design Shopping Cart Interface | Create a user - friendly shopping cart interface that displays added products , quantities , and prices .
| Add to Cart Functionality | Implement the ability for users to add products to their shopping cart from the product catalog .
| Remove from Cart Functionality | Allow users to remove products from their shopping cart .
| Display Cart Contents | Show a list of products in the shopping cart with details like name , quantity , price , and subtotal .
| Calculate Cart Total | Calculate and display the total price of all items in the shopping cart .
| Update Quantity | Enable users to update the quantity of items in their cart , adjusting the subtotal and total price .
| Proceed to Checkout | Create a " Proceed to Checkout " button that allows users to move to the checkout process .
| Implement Checkout Process ( Optional ) | Develop a complete checkout process , including user information , shipping , and payment .
| Save Cart Data ( Optional ) | Implement a way to save the shopping cart data for users who are logged in or using persistent carts .
| Apply Discounts and Coupons ( Optional ) | Include the ability for users to apply discounts or coupons to their cart total .
| Empty Cart | Provide an option for users to clear their entire shopping cart .
| Continue Shopping | Add a " Continue Shopping " button to let users go back to the product catalog .
| Handle Out - of - Stock Items ( Optional ) | Notify users and handle cases where a product becomes out of stock after being added to the cart .
| Mobile Responsiveness ( Optional ) | Ensure the shopping cart interface is responsive and usable on mobile devices .
| Guest Checkout ( Optional ) | Allow users to check out as guests without requiring user registration .
| Order Confirmation ( Optional ) | Display an order confirmation page after successful checkout with order details and a receipt .
| User Authentication ( Optional ) | Implement user authentication to associate carts with user accounts for registered users .
CHECK OUT & PAYMENT | Collect Shipping Information | Design and implement forms for users to enter shipping details, including address and contact information.
| Validate Shipping Information | Implement validation checks on shipping information to ensure accuracy and completeness.
| Provide Payment Options | Offer various payment options, including credit card, debit card, net banking, cash on delivery, etc.
| Implement Payment Gateway Integration | Integrate a payment gateway to facilitate secure and real-time payment processing.
| Calculate Order Total | Calculate the total order amount, including product prices, taxes, and shipping fees.
| Display Order Summary | Show users an order summary, including itemized details, shipping costs, and the total amount to be paid.
| Secure Payment Handling | Implement security measures to protect payment data during transmission and storage.
| Handle Payment Errors | Create error handling mechanisms to address payment failures and provide clear error messages to users.
| Confirm Order | Allow users to review their order, payment method, and shipping details before confirming the purchase.
| Place Order | Execute the payment transaction and place the order once the user confirms their purchase.
| Order Confirmation Page | Display an order confirmation page with a summary, order number, and confirmation message to the user.
| Send Order Confirmation Email | Send a confirmation email to the user with details of their order , estimated delivery date , and payment receipt .
| Guest Checkout ( Optional ) | Allow users to check out as guests without requiring user registration .
| User Authentication ( Optional ) | Implement user authentication to associate orders with user accounts for registered users .
| Handle Multiple Payment Gateways ( Optional ) | If offering multiple payment gateways , configure and manage their integration .
| Handling Refunds and Returns ( Optional ) | Develop processes for handling refund requests and returns , including tracking return status and refund processing .
| Compliance with Payment Regulations ( Optional ) | Ensure compliance with payment industry regulations , such as PCI DSS , if applicable .
ORDER | Design Order History Interface | Create a user interface that allows users to view their order history , including past and current orders .
| Store Order Data | Set up a database or data storage system to securely store order information , including order items , dates , and statuses .
| Send Order Confirmation Emails | Automate the sending of order confirmation emails to users after a successful purchase .
| Implement Order Tracking | Provide an order tracking system that allows users to monitor the status and progress of their orders .
| Display Order Detall | Cre detalled er view that displays order items , quantities , prices , shipping details , and total cost .
| Order Status Updates | implement mechanisms for updating and displaying order statuses , Including " Processing , " " Shipped , " " Delivered , " etc.
| Tracking Information ( Optional ) | Offer shipment tracking Information from third - party carriers ( e.g. , FedEx , UPS ) If applicable .
| Handling Returns and Refunds ( Optional ) | Develop processes for managing return requests , processing refunds , and updating order status accordingly .
| Print Order Invoices ( Optional ) | Allow users to generate and print invoices for their orders for record - keeping purposes .
| Order Cancellation ( Optional ) | implement a system for users to request order cancellations and update order status accordingly .
| Notifications and Alerts ( Optional ) | Send email or push notifications to users regarding order status changes or delays in shipping .
| Order Export ( Optional ) | Provide an option for users to export their order history in downloadable formats ( e.g. , PDF , CSV ) .
| Mobile Responsiveness ( Optional ) | Ensure the order history Interface is responsive and usable on mobile devices .
| User Authentication ( Optional ) | Implement user authentication to associate orders with user accounts for registered users .
| Customer Support Integration ( Optional ) | integrate customer support tools or chat for users to inquire about their orders or request assistance .